ORBITAL DYNAMICS TECHNOLOGIES

Enterprise Risk Intelligence

CONSOLIDATED RISK REPORT

Risk Influence Map Analysis

Report Date: 2026-02-27

Classification: CONFIDENTIAL

RIM Application v3.2 Export

| Programs | Total Risks | Security Risks |
| --- | --- | --- |
| HORIZON-LEO ¦ AURORA-GEO | 48 | 14 |

# Table of Contents

# PART I: EXECUTIVE COMMITTEE REPORT

This section provides the Executive Committee with a strategic overview of the enterprise risk landscape, highlighting the most critical threats to ODT business objectives and the effectiveness of the current mitigation portfolio.

## 1.1 Executive Risk Dashboard

| Metric | Value | Assessment |
| --- | --- | --- |
| Total Risk Portfolio | 48 | 48 active/contingent risks tracked |
| Business Risks | 17 | 5 corporate + 7 HORIZON + 5 AURORA |
| Operational Risks | 31 | Including 14 security-specific risks |
| Critical Exposure (>=50) | 3 | Within expected range |
| High Exposure (35-49) | 24 | Active monitoring required |
| Mitigation Coverage | 21 mitigations / 36 links | 12 implemented, 8 in progress |
| Top Program Objectives | 6 | 14 risk-to-TPO impact links identified |
| Influence Network Density | 44 causal links | Interconnected risk propagation modeled |

## 1.2 Top 10 Risks by Exposure

The following table presents the ten highest-exposure risks across the entire enterprise, ranked by their composite exposure score (Probability x Impact). These risks demand the most immediate executive attention and resource allocation.

| ID | Risk Name | Level | Scope | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RC-01 | Failure to achieve EBITDA positive by 2028 | Business | Company | 6.0 | 10.0 | 60 | CEO |
| RH-01 | Phase 3 launch schedule delay | Business | HORIZON-LEO | 7.0 | 8.0 | 56 | VP Launch Operations |
| RC-02 | Cash runway exhaustion before revenue ramp | Business | Company | 5.0 | 10.0 | 50 | CFO |
| ROH-01 | Key engineering talent attrition | Operational | Company | 7.0 | 7.0 | 49 | HR Director |
| RH-04 | Loss of competitive positioning vs mega-constellations | Business | HORIZON-LEO | 6.0 | 8.0 | 48 | CTO |
| ROL-01 | Launch vehicle availability gap | Operational | HORIZON-LEO | 6.0 | 8.0 | 48 | VP Launch Operations |
| RA-03 | Optical inter-satellite link technology maturation failure | Business | AURORA-GEO | 5.0 | 9.0 | 45 | CTO |
| SEC-04 | Ransomware attack on ground segment infrastructure | Operational | HORIZON-LEO | 5.0 | 9.0 | 45 | CISO |
| SEC-06 | Engineering data exfiltration by state-sponsored actor | Operational | Company | 5.0 | 9.0 | 45 | CISO |
| RH-03 | Corporate segment revenue target miss | Business | HORIZON-LEO | 6.0 | 7.0 | 42 | VP Sales |

## 1.3 Strategic Objective Threat Assessment

Each Top Program Objective (TPO) has been mapped to the business risks that could impair its achievement. The table below summarizes the threat landscape per objective.

| Ref | Objective | Cluster | Scope | Threats | Highest Impact |
| --- | --- | --- | --- | --- | --- |
| TPO-01 | Achieve EBITDA positive by Q4 2028 | Financial Performance |  | 3 | Critical |
| TPO-02 | Complete Phase 3 deployment by Q2 2027 | Programme Delivery |  | 2 | Critical |
| TPO-03 | Secure FCC full operational license by Q3 2026 | Regulatory |  | 2 | Critical |
| TPO-04 | Win first $10M+ Government contract by Q4 2026 | Commercial |  | 2 | Critical |
| TPO-05 | AURORA-GEO pass PDR gate by Q1 2027 | Programme Delivery |  | 3 | Critical |
| TPO-06 | Maintain zero debris generation incidents | Safety & Compliance |  | 2 | High |

## 1.4 Executive Recommendations

1. Accelerate RF dual-sourcing: The confluence of supply chain risks (RH-05, RO-06, RO-07) represents the highest concentration of cascading exposure. The RF component dual-sourcing qualification (MIT-01) must be fast-tracked to Q2 2026.

2. Reinforce satellite TT&C cybersecurity: The APT risk on satellite command systems (SEC-02) carries a Critical exposure of 40 with direct cascade to on-orbit performance and IP compromise. The Zero Trust TT&C architecture (MIT-04) should receive priority funding.

3. Secure AURORA funding commitment: AURORA-GEO Phase B funding (RA-02, exposure 50) represents an existential risk for portfolio diversification. A dedicated CEO-led engagement with ESA/NASA is recommended before Q2 2026 deadline.

4. Commission independent security assessment: With 14 security risks and multiple attack chain pathways identified, an external red team assessment of the satellite operations infrastructure should be commissioned within 60 days.

5. Strengthen customer acquisition pipeline: Enterprise customer acquisition miss (RH-04, exposure 48) directly threatens the EBITDA target. Commercial team resourcing and channel partner acceleration need executive sponsorship.

# PART II: RISK MANAGER REPORT

This section provides the Enterprise Risk Manager with a detailed analytical view of the risk portfolio, including influence network analysis, mitigation coverage gaps, and portfolio health metrics.

## 2.1 Complete Risk Register by Scope

### 2.1.1 Company-Level Risks

8 risks at the corporate level, owned by the Executive Committee and affecting ODT as a whole.

| ID | Risk Name | Level | Scope | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RC-01 | Failure to achieve EBITDA positive by 2028 | Business | Company | 6.0 | 10.0 | 60 | CEO |
| RC-02 | Cash runway exhaustion before revenue ramp | Business | Company | 5.0 | 10.0 | 50 | CFO |
| ROH-01 | Key engineering talent attrition | Operational | Company | 7.0 | 7.0 | 49 | HR Director |
| SEC-06 | Engineering data exfiltration by state-sponsored actor | Operational | Company | 5.0 | 9.0 | 45 | CISO |
| RC-03 | Loss of investor confidence | Business | Company | 4.0 | 9.0 | 36 | CEO |
| RC-04 | Multi-jurisdiction regulatory non-compliance | Business | Company | 4.0 | 8.0 | 32 | VP Compliance & Quality |
| ROF-01 | Foreign exchange exposure on international contracts | Operational | Company | 6.0 | 5.0 | 30 | CFO |
| RC-05 | Reputational damage from on-orbit incident | Business | Company | 3.0 | 9.0 | 27 | CEO |

### 2.1.2 HORIZON-LEO Program Risks

34 risks specific to the operational HORIZON-LEO constellation program.

| ID | Risk Name | Status | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| RH-01 | Phase 3 launch schedule delay | Active | 7.0 | 8.0 | 56 | VP Launch Operations |
| RH-04 | Loss of competitive positioning vs mega-constellations | Active | 6.0 | 8.0 | 48 | CTO |
| ROL-01 | Launch vehicle availability gap | Active | 6.0 | 8.0 | 48 | VP Launch Operations |
| SEC-04 | Ransomware attack on ground segment infrastructure | Active | 5.0 | 9.0 | 45 | CISO |
| RH-03 | Corporate segment revenue target miss | Active | 6.0 | 7.0 | 42 | VP Sales |
| RH-05 | Government & Defense contract pipeline failure | Active | 5.0 | 8.0 | 40 | VP Sales |
| SEC-01 | APT attack on satellite command and control system | Active | 4.0 | 10.0 | 40 | CISO |
| ROE-01 | Payload reconfiguration software critical defect | Active | 4.0 | 9.0 | 36 | Lead Software Architect |
| ROM-01 | RF component sole-source supplier failure | Active | 4.0 | 9.0 | 36 | VP Manufacturing & Supply Chain |
| ROH-02 | ITAR-cleared personnel shortage | Active | 6.0 | 6.0 | 36 | HR Director |
| SEC-09 | Social engineering targeting launch operations staff | Active | 6.0 | 6.0 | 36 | CISO |
| SEC-14 | IT-to-OT lateral movement into ground segment | Active | 4.0 | 9.0 | 36 | CISO |
| RH-02 | On-orbit satellite performance degradation | Active | 5.0 | 7.0 | 35 | VP Engineering |
| ROE-02 | Thermal design margin exceedance on Phase 3 batch | Active | 5.0 | 7.0 | 35 | Thermal Subsystem Lead |
| ROM-02 | Battery supplier critical delivery delay | Active | 5.0 | 7.0 | 35 | VP Manufacturing & Supply Chain |
| SEC-05 | RF signal jamming and spoofing attack | Active | 5.0 | 7.0 | 35 | CISO |
| RH-07 | ITU frequency coordination failure | Active | 4.0 | 8.0 | 32 | VP Compliance & Quality |
| RH-06 | Ground segment capacity bottleneck | Contingent | 5.0 | 6.0 | 30 | VP Ground & Ops |
| ROC-01 | Key enterprise customer churn | Active | 5.0 | 6.0 | 30 | VP Sales |
| ROC-02 | Channel partner underperformance | Active | 6.0 | 5.0 | 30 | VP Sales |
| SEC-02 | Supply chain compromise - malicious firmware insertion | Active | 3.0 | 10.0 | 30 | CISO |
| SEC-10 | DDoS on customer portal and API gateway | Active | 6.0 | 5.0 | 30 | CISO |
| SEC-11 | Satellite telemetry interception and analysis | Active | 5.0 | 6.0 | 30 | CISO |
| SEC-12 | Unauthorized firmware modification via maintenance backdoor | Active | 3.0 | 10.0 | 30 | CISO |
| ROM-03 | Composite structure quality deviation | Active | 4.0 | 7.0 | 28 | Quality Manager |
| ROF-02 | On-orbit asset insurance coverage gap | Active | 4.0 | 7.0 | 28 | CFO |
| ROR-01 | FCC spectrum license conditions breach | Active | 3.0 | 9.0 | 27 | VP Compliance & Quality |
| SEC-03 | Insider threat - privileged TT&C access abuse | Active | 3.0 | 9.0 | 27 | CISO |
| ROI-01 | NOC system extended outage | Active | 3.0 | 8.0 | 24 | IT Director |
| ROM-04 | Clean room contamination event | Active | 3.0 | 7.0 | 21 | Plant Director |
| SEC-08 | Cloud provider compromise affecting NOC services | Active | 3.0 | 7.0 | 21 | CISO |
| ROL-02 | Orbital debris collision during deployment | Active | 2.0 | 10.0 | 20 | VP Launch Operations |
| SEC-13 | Cryptographic key compromise for satellite command auth | Active | 2.0 | 10.0 | 20 | CISO |
| SEC-07 | Physical security breach at ground station | Active | 2.0 | 8.0 | 16 | CISO |

### 2.1.3 AURORA-GEO Program Risks

6 risks specific to the early-development AURORA-GEO relay program.

| ID | Risk Name | Status | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| RA-03 | Optical inter-satellite link technology maturation failure | Active | 5.0 | 9.0 | 45 | CTO |
| RA-01 | PDR technical readiness delay | Active | 6.0 | 7.0 | 42 | AURORA Program Director |
| RA-02 | Development budget overrun | Active | 7.0 | 6.0 | 42 | CFO |
| ROE-03 | Optical terminal pointing accuracy failure | Active | 5.0 | 8.0 | 40 | AURORA Chief Engineer |
| RA-04 | Strategic partner withdrawal | Contingent | 4.0 | 9.0 | 36 | AURORA Program Director |
| RA-05 | ITAR export control blocking key partnerships | Active | 5.0 | 7.0 | 35 | VP Compliance & Quality |

## 2.2 Influence Network Analysis

The Risk Influence Map models directed causal relationships between risks. The table below shows the influence links organized by type, enabling understanding of how operational failures propagate to business consequences.

| Influence Type | Count | Description |
| --- | --- | --- |
| Level1 Op to Bus | 20 | Operational causes triggering business consequences |
| Level2 Bus to Bus | 12 | Business risk cascades to other business risks |
| Level3 Op to Op | 12 | Operational risk amplifying other operational risks |

### 2.2.1 Critical Influence Chains

The following chains represent the highest-impact propagation paths where a single operational failure can cascade to multiple business consequences:

| Source | Target | Strength | Cascade Description |
| --- | --- | --- | --- |
| ROE-01 | RH-02 | Critical | Payload software defect directly degrades satellite performance |
| ROE-03 | RA-03 | Critical | Pointing accuracy failure is the core technical risk for optical ISL maturation |
| ROM-01 | RH-01 | Critical | RF component supplier failure halts satellite production, directly delaying Phase 3 launches |
| ROL-01 | RH-01 | Critical | Launch vehicle unavailability directly blocks Phase 3 deployment schedule |
| ROL-02 | RC-05 | Critical | Debris collision would generate severe reputational damage |
| ROR-01 | RC-04 | Critical | FCC breach directly contributes to multi-jurisdiction compliance failure |
| SEC-01 | RC-05 | Critical | APT compromising satellite command would be catastrophic reputational event |
| SEC-04 | RH-02 | Critical | Ransomware on ground segment causes loss of constellation management |
| SEC-06 | RH-04 | Critical | IP exfiltration eliminates competitive technological advantage |
| RH-01 | RC-01 | Critical | Phase 3 delay pushes revenue ramp, directly threatening EBITDA timeline |
| RH-03 | RC-01 | Critical | Revenue miss directly impacts EBITDA achievement |
| RC-02 | RC-03 | Critical | Cash runway exhaustion directly triggers investor confidence loss |
| RC-05 | RC-03 | Critical | Reputational damage directly erodes investor confidence |
| RA-03 | RA-01 | Critical | Optical technology maturation failure blocks PDR readiness |
| SEC-14 | SEC-01 | Critical | IT-to-OT lateral movement enables access to satellite command systems |
| SEC-13 | SEC-12 | Critical | Compromised command keys enable unauthorized firmware modification |

## 2.3 Mitigation Portfolio Analysis

| Total | Dedicated | Inherited | Baseline | Coverage Links |
| --- | --- | --- | --- | --- |
| 21 | 12 | 4 | 5 | 36 |

### 2.3.1 Unmitigated or Under-Mitigated Risks

16 risks currently have NO mitigation coverage in the register. These represent potential blind spots in the control framework:

| ID | Risk Name | Level | Scope | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RC-01 | Failure to achieve EBITDA positive by 2028 | Business | Company | 6.0 | 10.0 | 60 | CEO |
| RH-03 | Corporate segment revenue target miss | Business | HORIZON-LEO | 6.0 | 7.0 | 42 | VP Sales |
| RA-01 | PDR technical readiness delay | Business | AURORA-GEO | 6.0 | 7.0 | 42 | AURORA Program Director |
| RH-05 | Government & Defense contract pipeline failure | Business | HORIZON-LEO | 5.0 | 8.0 | 40 | VP Sales |
| RC-03 | Loss of investor confidence | Business | Company | 4.0 | 9.0 | 36 | CEO |
| RA-04 | Strategic partner withdrawal | Business | AURORA-GEO | 4.0 | 9.0 | 36 | AURORA Program Director |
| ROH-02 | ITAR-cleared personnel shortage | Operational | HORIZON-LEO | 6.0 | 6.0 | 36 | HR Director |
| RH-02 | On-orbit satellite performance degradation | Business | HORIZON-LEO | 5.0 | 7.0 | 35 | VP Engineering |
| ROM-02 | Battery supplier critical delivery delay | Operational | HORIZON-LEO | 5.0 | 7.0 | 35 | VP Manufacturing & Supply Chain |
| RH-07 | ITU frequency coordination failure | Business | HORIZON-LEO | 4.0 | 8.0 | 32 | VP Compliance & Quality |
| RH-06 | Ground segment capacity bottleneck | Business | HORIZON-LEO | 5.0 | 6.0 | 30 | VP Ground & Ops |
| ROC-02 | Channel partner underperformance | Operational | HORIZON-LEO | 6.0 | 5.0 | 30 | VP Sales |
| ROF-01 | Foreign exchange exposure on international contracts | Operational | Company | 6.0 | 5.0 | 30 | CFO |
| ROF-02 | On-orbit asset insurance coverage gap | Operational | HORIZON-LEO | 4.0 | 7.0 | 28 | CFO |
| RC-05 | Reputational damage from on-orbit incident | Business | Company | 3.0 | 9.0 | 27 | CEO |

## 2.4 Contingent Risks Watch List

The following risks are in Contingent status, meaning they will activate only if specific conditions are met. These require monitoring of trigger conditions:

RH-06 - Ground segment capacity bottleneck

Activation condition: If Phase 3 satellites exceed 40 active beams per satellite in high-demand zones

RA-04 - Strategic partner withdrawal

Activation condition: If partner M&A activity is confirmed or strategic review initiated

# PART III: PROGRAM MANAGERS REPORT

This section provides each Program Manager with a focused view of their programme risk landscape, including programme-specific operational risks, supply chain dependencies, and schedule threat analysis.

## 3.1 HORIZON-LEO Constellation Program

HORIZON-LEO is the operational flagship program deploying an 80-satellite LEO constellation for global broadband. Phase 1 (12 satellites) is operational. Phase 2 (20 satellites) deployment is in active preparation.

### 3.1.1 Programme Risk Summary

| Business Risks | Operational Risks | Security Risks | Avg. Exposure |
| --- | --- | --- | --- |
| 7 | 27 | 13 | 32.7 |

### 3.1.2 HORIZON-LEO Business Risk Register

| ID | Risk Name | Status | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| RH-01 | Phase 3 launch schedule delay | Active | 7.0 | 8.0 | 56 | VP Launch Operations |
| RH-04 | Loss of competitive positioning vs mega-constellations | Active | 6.0 | 8.0 | 48 | CTO |
| RH-03 | Corporate segment revenue target miss | Active | 6.0 | 7.0 | 42 | VP Sales |
| RH-05 | Government & Defense contract pipeline failure | Active | 5.0 | 8.0 | 40 | VP Sales |
| RH-02 | On-orbit satellite performance degradation | Active | 5.0 | 7.0 | 35 | VP Engineering |
| RH-07 | ITU frequency coordination failure | Active | 4.0 | 8.0 | 32 | VP Compliance & Quality |
| RH-06 | Ground segment capacity bottleneck | Contingent | 5.0 | 6.0 | 30 | VP Ground & Ops |

### 3.1.3 HORIZON-LEO Operational Risk Register

| ID | Risk Name | Status | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| ROL-01 | Launch vehicle availability gap | Active | 6.0 | 8.0 | 48 | VP Launch Operations |
| SEC-04 | Ransomware attack on ground segment infrastructure | Active | 5.0 | 9.0 | 45 | CISO |
| SEC-01 | APT attack on satellite command and control system | Active | 4.0 | 10.0 | 40 | CISO |
| ROE-01 | Payload reconfiguration software critical defect | Active | 4.0 | 9.0 | 36 | Lead Software Architect |
| ROM-01 | RF component sole-source supplier failure | Active | 4.0 | 9.0 | 36 | VP Manufacturing & Supply Chain |
| ROH-02 | ITAR-cleared personnel shortage | Active | 6.0 | 6.0 | 36 | HR Director |
| SEC-09 | Social engineering targeting launch operations staff | Active | 6.0 | 6.0 | 36 | CISO |
| SEC-14 | IT-to-OT lateral movement into ground segment | Active | 4.0 | 9.0 | 36 | CISO |
| ROE-02 | Thermal design margin exceedance on Phase 3 batch | Active | 5.0 | 7.0 | 35 | Thermal Subsystem Lead |
| ROM-02 | Battery supplier critical delivery delay | Active | 5.0 | 7.0 | 35 | VP Manufacturing & Supply Chain |
| SEC-05 | RF signal jamming and spoofing attack | Active | 5.0 | 7.0 | 35 | CISO |
| ROC-01 | Key enterprise customer churn | Active | 5.0 | 6.0 | 30 | VP Sales |
| ROC-02 | Channel partner underperformance | Active | 6.0 | 5.0 | 30 | VP Sales |
| SEC-02 | Supply chain compromise - malicious firmware insertion | Active | 3.0 | 10.0 | 30 | CISO |
| SEC-10 | DDoS on customer portal and API gateway | Active | 6.0 | 5.0 | 30 | CISO |
| SEC-11 | Satellite telemetry interception and analysis | Active | 5.0 | 6.0 | 30 | CISO |
| SEC-12 | Unauthorized firmware modification via maintenance backdoor | Active | 3.0 | 10.0 | 30 | CISO |
| ROM-03 | Composite structure quality deviation | Active | 4.0 | 7.0 | 28 | Quality Manager |
| ROF-02 | On-orbit asset insurance coverage gap | Active | 4.0 | 7.0 | 28 | CFO |
| ROR-01 | FCC spectrum license conditions breach | Active | 3.0 | 9.0 | 27 | VP Compliance & Quality |
| SEC-03 | Insider threat - privileged TT&C access abuse | Active | 3.0 | 9.0 | 27 | CISO |
| ROI-01 | NOC system extended outage | Active | 3.0 | 8.0 | 24 | IT Director |
| ROM-04 | Clean room contamination event | Active | 3.0 | 7.0 | 21 | Plant Director |
| SEC-08 | Cloud provider compromise affecting NOC services | Active | 3.0 | 7.0 | 21 | CISO |
| ROL-02 | Orbital debris collision during deployment | Active | 2.0 | 10.0 | 20 | VP Launch Operations |
| SEC-13 | Cryptographic key compromise for satellite command auth | Active | 2.0 | 10.0 | 20 | CISO |
| SEC-07 | Physical security breach at ground station | Active | 2.0 | 8.0 | 16 | CISO |

### 3.1.4 HORIZON-LEO Objectives at Risk

## 3.2 AURORA-GEO Relay Satellite Program

AURORA-GEO is an early-development program for a GEO relay satellite with optical inter-satellite links, co-funded by ESA/NASA. Currently in Phase A/B pre-development with PDR targeted for Q4 2026.

### 3.2.1 AURORA-GEO Risk Register

| ID | Risk Name | Status | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| RA-03 | Optical inter-satellite link technology maturation failure | Active | 5.0 | 9.0 | 45 | CTO |
| RA-01 | PDR technical readiness delay | Active | 6.0 | 7.0 | 42 | AURORA Program Director |
| RA-02 | Development budget overrun | Active | 7.0 | 6.0 | 42 | CFO |
| ROE-03 | Optical terminal pointing accuracy failure | Active | 5.0 | 8.0 | 40 | AURORA Chief Engineer |
| RA-04 | Strategic partner withdrawal | Contingent | 4.0 | 9.0 | 36 | AURORA Program Director |
| RA-05 | ITAR export control blocking key partnerships | Active | 5.0 | 7.0 | 35 | VP Compliance & Quality |

### 3.2.2 AURORA-GEO Objectives at Risk

### 3.2.3 Key AURORA Mitigations

# PART IV: CHIEF INFORMATION SECURITY OFFICER REPORT

This section provides the CISO with a comprehensive view of the cybersecurity risk landscape, including threat taxonomy, attack chain analysis, mitigation coverage assessment, and recommendations for security posture improvement.

## 4.1 Security Risk Portfolio Overview

ODT maintains 14 security-specific operational risks in the enterprise risk register. These cover the full spectrum from state-sponsored threats to insider risks, physical security, and supply chain attacks.

| Total Security Risks | Active | Contingent | Critical Exposure |
| --- | --- | --- | --- |
| 14 | 14 | 0 | 3 |

## 4.2 Security Risk Register

| ID | Risk Name | Level | Scope | P | I | Exp. | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SEC-04 | Ransomware attack on ground segment infrastructure | Operational | HORIZON-LEO | 5.0 | 9.0 | 45 | CISO |
| SEC-06 | Engineering data exfiltration by state-sponsored actor | Operational | Company | 5.0 | 9.0 | 45 | CISO |
| SEC-01 | APT attack on satellite command and control system | Operational | HORIZON-LEO | 4.0 | 10.0 | 40 | CISO |
| SEC-09 | Social engineering targeting launch operations staff | Operational | HORIZON-LEO | 6.0 | 6.0 | 36 | CISO |
| SEC-14 | IT-to-OT lateral movement into ground segment | Operational | HORIZON-LEO | 4.0 | 9.0 | 36 | CISO |
| SEC-05 | RF signal jamming and spoofing attack | Operational | HORIZON-LEO | 5.0 | 7.0 | 35 | CISO |
| SEC-02 | Supply chain compromise - malicious firmware insertion | Operational | HORIZON-LEO | 3.0 | 10.0 | 30 | CISO |
| SEC-10 | DDoS on customer portal and API gateway | Operational | HORIZON-LEO | 6.0 | 5.0 | 30 | CISO |
| SEC-11 | Satellite telemetry interception and analysis | Operational | HORIZON-LEO | 5.0 | 6.0 | 30 | CISO |
| SEC-12 | Unauthorized firmware modification via maintenance backdoor | Operational | HORIZON-LEO | 3.0 | 10.0 | 30 | CISO |
| SEC-03 | Insider threat - privileged TT&C access abuse | Operational | HORIZON-LEO | 3.0 | 9.0 | 27 | CISO |
| SEC-08 | Cloud provider compromise affecting NOC services | Operational | HORIZON-LEO | 3.0 | 7.0 | 21 | CISO |
| SEC-13 | Cryptographic key compromise for satellite command auth | Operational | HORIZON-LEO | 2.0 | 10.0 | 20 | CISO |
| SEC-07 | Physical security breach at ground station | Operational | HORIZON-LEO | 2.0 | 8.0 | 16 | CISO |

## 4.3 Attack Chain Analysis

The Risk Influence Map reveals several multi-step attack chains where security risks cascade through operational and business layers. Understanding these chains is essential for defense-in-depth prioritization.

Attack Origin: SEC-01 - APT attack on satellite command and control system

-> RC-05 (Reputational damage from on-orbit incident) [Critical]: APT compromising satellite command would be catastrophic reputational event

Attack Origin: SEC-04 - Ransomware attack on ground segment infrastructure

-> RH-02 (On-orbit satellite performance degradation) [Critical]: Ransomware on ground segment causes loss of constellation management

Attack Origin: SEC-06 - Engineering data exfiltration by state-sponsored actor

-> RH-04 (Loss of competitive positioning vs mega-constellations) [Critical]: IP exfiltration eliminates competitive technological advantage

Attack Origin: SEC-05 - RF signal jamming and spoofing attack

-> RH-03 (Corporate segment revenue target miss) [Strong]: RF jamming degrades service quality causing customer revenue impact

Attack Origin: SEC-10 - DDoS on customer portal and API gateway

-> RH-03 (Corporate segment revenue target miss) [Moderate]: DDoS on portal disrupts customer onboarding and billing

Attack Origin: SEC-09 - Social engineering targeting launch operations staff

-> SEC-04 (Ransomware attack on ground segment infrastructure) [Strong]: Social engineering provides initial access vector for ransomware deployment

-> SEC-01 (APT attack on satellite command and control system) [Moderate]: Social engineering credentials enable initial foothold for APT campaign

Attack Origin: SEC-14 - IT-to-OT lateral movement into ground segment

-> SEC-01 (APT attack on satellite command and control system) [Critical]: IT-to-OT lateral movement enables access to satellite command systems

-> SEC-04 (Ransomware attack on ground segment infrastructure) [Strong]: IT-to-OT pivot extends ransomware blast radius to ground segment

Attack Origin: SEC-13 - Cryptographic key compromise for satellite command auth

-> SEC-12 (Unauthorized firmware modification via maintenance backdoor) [Critical]: Compromised command keys enable unauthorized firmware modification

Attack Origin: SEC-03 - Insider threat - privileged TT&C access abuse

-> SEC-13 (Cryptographic key compromise for satellite command auth) [Strong]: Insider with privileged access can extract cryptographic keys

Attack Origin: SEC-02 - Supply chain compromise - malicious firmware insertion

-> SEC-12 (Unauthorized firmware modification via maintenance backdoor) [Strong]: Supply chain malicious firmware is unauthorized modification by nature

Attack Origin: SEC-08 - Cloud provider compromise affecting NOC services

-> ROI-01 (NOC system extended outage) [Strong]: Cloud provider compromise causes NOC service outage

Attack Origin: SEC-07 - Physical security breach at ground station

-> SEC-14 (IT-to-OT lateral movement into ground segment) [Moderate]: Physical breach at ground station can provide network access point for IT-to-OT pivot

Attack Origin: SEC-11 - Satellite telemetry interception and analysis

-> SEC-05 (RF signal jamming and spoofing attack) [Moderate]: Telemetry intelligence informs targeted jamming/spoofing attacks

## 4.4 Security Mitigation Coverage

| ID | Mitigation | Type | Status | Risks Covered |
| --- | --- | --- | --- | --- |
| MIT-04 | Ground segment Zero Trust architecture | Dedicated | In Progress | SEC-14, SEC-04 |
| MIT-05 | Satellite command authentication hardening | Dedicated | In Progress | SEC-01, SEC-13, SEC-12 |
| MIT-10 | Supply chain hardware integrity verification | Dedicated | Proposed | SEC-02 |
| MIT-11 | Anti-jamming adaptive beam-forming | Dedicated | In Progress | SEC-05 |
| MIT-12 | Ransomware-specific incident response plan | Dedicated | Implemented | SEC-04 |
| MIT-13 | Corporate SOC 24/7 monitoring | Inherited | Implemented | SEC-01, SEC-14, SEC-10 |
| MIT-16 | Corporate security awareness training | Inherited | Implemented | SEC-09, SEC-03 |
| MIT-18 | NIST Cybersecurity Framework implementation | Baseline | Implemented | SEC-06, SEC-08 |
| MIT-21 | ISO 27001 ISMS certification | Baseline | Implemented | SEC-06, SEC-07, SEC-11 |

### 4.4.1 Security Risks Without Dedicated Mitigation

All security risks have at least one mitigation assigned.

## 4.5 Cybersecurity Objective Status

## 4.6 CISO Recommendations

Priority 1 - TT&C Security Hardening: Complete the Zero Trust architecture implementation (MIT-04) for satellite TT&C systems by Q3 2026. The APT risk (SEC-02, exposure 40) with Critical strength influence on both IP compromise and on-orbit performance represents the single highest-impact security scenario.

Priority 2 - Supply Chain Firmware Integrity: Implement a formal firmware signing and verification program for all third-party satellite subsystem components. Risk SEC-04 (firmware injection, exposure 30) has a demonstrated cascade path through SEC-10 (USB malware) and could create undetectable persistent backdoors.

Priority 3 - Insider Threat Program Enhancement: Formalize the insider threat detection program beyond current PAM controls. SEC-03 (privileged admin exfiltration, exposure 27) has a Critical influence path directly to strategic IP compromise (RC-05). Deploy UEBA analytics on engineering workstations.

Priority 4 - Ground Station Physical Security Audit: Commission independent physical security assessments of all 4 primary ground stations. SEC-13 (physical breach, exposure 16) cascades to SEC-12 (data exfiltration) and could bypass all logical controls.

Priority 5 - Red Team Exercise: Conduct a full-scope red team assessment combining physical, social engineering, and cyber attack vectors against the satellite operations chain within 90 days.