## Risks
id | name | level | categories | description | status | origin | activation_condition | activation_decision_date | owner | probability | impact | exposure | current_score_type
RS-02 | Series production start delay | Strategic | ['Programme', 'Industrial'] | Risk of delay in starting series production scheduled for 2030 | Active | New |  |  | VP Industrialization | 7 | 8 | 56 | Qualitative_4x4
RS-05 | Fuel supply tension | Strategic | ['Programme', 'Supply Chain'] | Risk of geopolitical tension affecting Type A fuel supply | Contingent | Legacy | If Type A enriched uranium fuel is selected in Q3 2026 decision | 2026-09-30 | VP Supply Chain | 8 | 7 | 56 | Qualitative_4x4
RS-01 | Failure to achieve profitability target | Strategic | ['Programme'] | Risk of not achieving the required profitability level within the specified timeframe | Active | New |  |  | Program Director | 6 | 9 | 54 | Qualitative_4x4
RS-06 | Intellectual property compromise | Strategic | ['Programme', 'Product'] | Risk of critical intellectual property leakage or theft via digital backbone | Contingent | New | If digital backbone architecture opens to external ecosystem | 2026-09-30 | CISO | 6 | 9 | 54 | Qualitative_4x4
RO-01 | Critical control system component supplier failure | Operational | ['Supply Chain', 'Product'] | Failure or bankruptcy of sole supplier of critical control system components | Active | New |  |  | Critical Procurement Manager | 6 | 8 | 48 | Qualitative_4x4
RS-03 | Loss of competitive technological advantage | Strategic | ['Programme', 'Product'] | Risk of losing technological lead against SMR competitors | Active | New |  |  | CTO | 5 | 9 | 45 | Qualitative_4x4
RS-07 | Insufficient production capacity | Strategic | ['Industrial'] | Risk of production capacity being insufficient to achieve nominal rate | Active | New |  |  | Plant Director | 6 | 7 | 42 | Qualitative_4x4
RS-08 | Development budget overrun | Strategic | ['Programme'] | Risk of significant overrun of allocated development budget | Active | Legacy |  |  | CFO | 7 | 6 | 42 | Qualitative_4x4
RO-04 | Critical supplier certification delay | Operational | ['Supply Chain'] | Delay in obtaining required certifications for a strategic supplier | Active | New |  |  | Supply Chain Manager | 7 | 6 | 42 | Qualitative_4x4
RO-05 | Key R&D team competency loss | Operational | ['Programme', 'Product'] | Departure of critical R&D experts to competitors | Active | Legacy |  |  | HR Director | 6 | 7 | 42 | Qualitative_4x4
RO-02 | Cyberattack on PLM infrastructure | Operational | ['Programme', 'Product'] | Targeted attack on PLM system causing data leakage or unavailability | Active | Legacy |  |  | CISO | 5 | 8 | 40 | Qualitative_4x4
RO-06 | Critical safety embedded software bug | Operational | ['Product'] | Undetected critical software defect in control-command system | Active | New |  |  | Lead Embedded Developer | 4 | 9 | 36 | Qualitative_4x4
RO-03 | Manufacturing process quality drift | Operational | ['Industrial'] | Progressive degradation of manufacturing process quality | Active | New |  |  | Quality Manager | 5 | 7 | 35 | Qualitative_4x4
RS-04 | Regulatory safety non-compliance | Strategic | ['Programme', 'Product'] | Risk of non-compliance with nuclear safety standards | Active | Legacy |  |  | Safety Manager | 3 | 10 | 30 | Qualitative_4x4
RO-07 | Extended digital infrastructure unavailability | Operational | ['Programme'] | Major failure or crash of digital backbone infrastructure | Active | Legacy |  |  | IT Director | 4 | 6 | 24 | Qualitative_4x4

## Influences
id | source_id | source_name | source_level | target_id | target_name | target_level | influence_type | strength | description | confidence
INF-18 | RO-04 | Critical supplier certification delay | Operational | RO-01 | Critical control system component supplier failure | Operational | Level3_Op_to_Op | Weak | Certification delays generally correlate with other supplier failures | 0.6
INF-11 | RS-05 | Fuel supply tension | Strategic | RS-02 | Series production start delay | Strategic | Level2_Strat_to_Strat | Strong | Fuel supply tension delays first reactor startup | 0.8
INF-04 | RO-04 | Critical supplier certification delay | Operational | RS-02 | Series production start delay | Strategic | Level1_Op_to_Strat | Strong | Supplier certification delay slows supply chain qualification | 0.8
INF-13 | RS-07 | Insufficient production capacity | Strategic | RS-01 | Failure to achieve profitability target | Strategic | Level2_Strat_to_Strat | Strong | Capacity insufficiency limits potential revenues | 0.85
INF-09 | RS-03 | Loss of competitive technological advantage | Strategic | RS-01 | Failure to achieve profitability target | Strategic | Level2_Strat_to_Strat | Strong | Loss of technological advantage reduces margins and market share | 0.85
INF-12 | RS-06 | Intellectual property compromise | Strategic | RS-03 | Loss of competitive technological advantage | Strategic | Level2_Strat_to_Strat | Strong | IP compromise causes loss of competitive technological advantage | 0.9
INF-05 | RO-05 | Key R&D team competency loss | Operational | RS-03 | Loss of competitive technological advantage | Strategic | Level1_Op_to_Strat | Strong | Loss of key competencies slows development and innovation | 0.85
INF-02 | RO-02 | Cyberattack on PLM infrastructure | Operational | RS-06 | Intellectual property compromise | Strategic | Level1_Op_to_Strat | Strong | A cyberattack on PLM directly exposes critical intellectual property | 0.85
INF-16 | RO-02 | Cyberattack on PLM infrastructure | Operational | RO-07 | Extended digital infrastructure unavailability | Operational | Level3_Op_to_Op | Strong | Cyberattack causes digital infrastructure unavailability | 0.9
INF-07 | RO-07 | Extended digital infrastructure unavailability | Operational | RS-02 | Series production start delay | Strategic | Level1_Op_to_Strat | Moderate | Digital backbone unavailability slows product development | 0.7
INF-14 | RS-08 | Development budget overrun | Strategic | RS-01 | Failure to achieve profitability target | Strategic | Level2_Strat_to_Strat | Moderate | Budget overrun directly reduces operating margin | 1
INF-15 | RO-01 | Critical control system component supplier failure | Operational | RO-03 | Manufacturing process quality drift | Operational | Level3_Op_to_Op | Moderate | Supplier failure forces use of less reliable backup components | 0.7
INF-17 | RO-05 | Key R&D team competency loss | Operational | RO-06 | Critical safety embedded software bug | Operational | Level3_Op_to_Op | Moderate | Loss of competencies increases risk of bug introduction | 0.75
INF-10 | RS-04 | Regulatory safety non-compliance | Strategic | RS-02 | Series production start delay | Strategic | Level2_Strat_to_Strat | Critical | Safety non-compliance blocks production authorization | 1
INF-01 | RO-01 | Critical control system component supplier failure | Operational | RS-02 | Series production start delay | Strategic | Level1_Op_to_Strat | Critical | Critical component supplier failure directly blocks series production | 0.9
INF-08 | RS-02 | Series production start delay | Strategic | RS-01 | Failure to achieve profitability target | Strategic | Level2_Strat_to_Strat | Critical | Production delay directly impacts revenue and therefore profitability | 1
INF-06 | RO-06 | Critical safety embedded software bug | Operational | RS-04 | Regulatory safety non-compliance | Strategic | Level1_Op_to_Strat | Critical | A critical bug in embedded software directly compromises safety | 1
INF-03 | RO-03 | Manufacturing process quality drift | Operational | RS-04 | Regulatory safety non-compliance | Strategic | Level1_Op_to_Strat | Critical | Quality drift compromises compliance with nuclear safety standards | 0.95

## TPOs
id | reference | name | cluster | description
TPO-01 | TPO-01 | Achieve profitability by 2032 | Business Efficiency | Positive ROI target and operating margin > 15% by end of 2032
TPO-02 | TPO-02 | NRC safety certification before end of 2029 | Safety | Obtain all nuclear safety certifications required by the NRC to authorize commissioning
TPO-03 | TPO-03 | Series production start Q1 2030 | Industrial Efficiency | Launch series production of the first SMR with an initial rate of 2 units/year

## TPO_Impacts
id | risk_id | risk_name | tpo_id | tpo_reference | tpo_name | impact_level | description
IMP-08 | RS-03 | Loss of competitive technological advantage | TPO-01 | TPO-01 | Achieve profitability by 2032 | Medium | Loss of technological advantage reduces pricing power and margins
IMP-07 | RS-08 | Development budget overrun | TPO-01 | TPO-01 | Achieve profitability by 2032 | High | Budget overrun directly degrades margin and ROI
IMP-02 | RS-02 | Series production start delay | TPO-01 | TPO-01 | Achieve profitability by 2032 | High | Production delay shifts revenue and impacts ROI
IMP-01 | RS-01 | Failure to achieve profitability target | TPO-01 | TPO-01 | Achieve profitability by 2032 | Critical | Direct impact: this risk directly threatens the profitability objective
IMP-04 | RS-04 | Regulatory safety non-compliance | TPO-02 | TPO-02 | NRC safety certification before end of 2029 | Critical | Direct impact: non-compliance prevents obtaining NRC certification
IMP-06 | RS-07 | Insufficient production capacity | TPO-03 | TPO-03 | Series production start Q1 2030 | High | Capacity insufficiency compromises achieving target production rate
IMP-05 | RS-04 | Regulatory safety non-compliance | TPO-03 | TPO-03 | Series production start Q1 2030 | High | Without safety certification, production start is blocked
IMP-03 | RS-02 | Series production start delay | TPO-03 | TPO-03 | Series production start Q1 2030 | Critical | Direct impact: this risk threatens the series production start objective

## Mitigations
id | name | type | status | description | owner | source_entity
MIT-10 | Corporate IT continuity plan | Inherited | Implemented | Disaster recovery infrastructure with RTO 4h and RPO 1h for critical systems | IT Director | Corporate IT Division
MIT-08 | Corporate budget management process | Inherited | Implemented | Application of corporate budget tracking process with monthly reviews and automatic alerts on deviations >5% | CFO | Corporate Finance Division
MIT-09 | Corporate shared SOC | Inherited | Implemented | 24/7 monitoring by corporate Security Operations Center with incident response capability <15min | CISO | Corporate IT Division
MIT-01 | Critical components dual-sourcing strategy | Dedicated | In Progress | Qualification of a second supplier for all critical control system components with signed framework contracts | Critical Procurement Manager
MIT-07 | Fuel source diversification | Dedicated | Proposed | Negotiation of long-term contracts with fuel suppliers across different geopolitical zones | VP Supply Chain
MIT-13 | IEC 61513 Nuclear I&C compliance | Baseline | In Progress | Systematic application of IEC 61513 standard for nuclear instrumentation and control systems | Lead Embedded Developer | IEC 61513:2011
MIT-12 | ISO 19443 Nuclear Quality certification | Baseline | In Progress | Quality system certification per ISO 19443 specific to nuclear supply chain | Quality Manager | ISO 19443:2018
MIT-06 | Independent safety code review | Dedicated | In Progress | Contract with independent third party for systematic safety-critical code review per DO-178C | Lead Embedded Developer
MIT-14 | NIS2 cybersecurity framework | Baseline | Implemented | Compliance with NIS2 directive for essential service operators in energy sector | CISO | EU Directive 2022/2555 (NIS2)
MIT-15 | NRC regulatory framework | Baseline | In Progress | Application of NRC framework for nuclear facilities with defined compliance milestones | Safety Manager | 10 CFR Part 50/52
MIT-04 | PLM Zero Trust architecture | Dedicated | Proposed | Redesign of PLM security architecture following Zero Trust model with micro-segmentation and continuous authentication | CISO
MIT-05 | Production contingency plan | Dedicated | Implemented | Detailed alternative ramp-up plan with identification of qualified backup subcontractors | VP Industrialization
MIT-02 | R&D talent retention program | Dedicated | Implemented | Retention package including long-term incentives, technical career paths and mentoring program for key experts | HR Director
MIT-03 | Real-time quality review system | Dedicated | In Progress | Deployment of IoT sensors and real-time dashboard for continuous monitoring of process quality parameters | Quality Manager
MIT-11 | Shared Innovation program | Inherited | Implemented | Access to patents and innovations from other group divisions via intellectual property sharing program | CTO | Corporate R&D Division

## Mitigates
id | mitigation_id | mitigation_name | mitigation_type | risk_id | risk_name | risk_level | effectiveness | description
MIG-16 | MIT-10 | Corporate IT continuity plan | Inherited | RO-07 | Extended digital infrastructure unavailability | Operational | Critical | Disaster recovery guarantees rapid recovery in case of major failure
MIG-13 | MIT-08 | Corporate budget management process | Inherited | RS-08 | Development budget overrun | Strategic | Medium | Rigorous tracking enables early deviation detection and corrective action
MIG-14 | MIT-09 | Corporate shared SOC | Inherited | RO-02 | Cyberattack on PLM infrastructure | Operational | High | 24/7 SOC enables rapid detection and response to intrusion attempts
MIG-15 | MIT-09 | Corporate shared SOC | Inherited | RO-07 | Extended digital infrastructure unavailability | Operational | Medium | Proactive monitoring allows anticipating certain failures and incidents
MIG-01 | MIT-01 | Critical components dual-sourcing strategy | Dedicated | RO-01 | Critical control system component supplier failure | Operational | High | Dual-sourcing allows switching to second supplier in case of primary supplier failure
MIG-02 | MIT-01 | Critical components dual-sourcing strategy | Dedicated | RS-02 | Series production start delay | Strategic | Medium | Securing supply chain reduces component-related delay risks
MIG-12 | MIT-07 | Fuel source diversification | Dedicated | RS-05 | Fuel supply tension | Strategic | High | Geographic diversification reduces exposure to tensions in any specific zone
MIG-20 | MIT-13 | IEC 61513 Nuclear I&C compliance | Baseline | RO-06 | Critical safety embedded software bug | Operational | High | IEC 61513 standard defines strict requirements for nuclear I&C systems development
MIG-21 | MIT-13 | IEC 61513 Nuclear I&C compliance | Baseline | RS-04 | Regulatory safety non-compliance | Strategic | Critical | IEC 61513 compliance is a prerequisite for I&C systems safety certification
MIG-19 | MIT-12 | ISO 19443 Nuclear Quality certification | Baseline | RO-04 | Critical supplier certification delay | Operational | Medium | ISO framework structures the supplier qualification process
MIG-18 | MIT-12 | ISO 19443 Nuclear Quality certification | Baseline | RO-03 | Manufacturing process quality drift | Operational | High | ISO 19443 framework mandates rigorous quality controls throughout supply chain
MIG-10 | MIT-06 | Independent safety code review | Dedicated | RO-06 | Critical safety embedded software bug | Operational | Critical | Independent review maximizes chances of detecting critical bugs before deployment
MIG-11 | MIT-06 | Independent safety code review | Dedicated | RS-04 | Regulatory safety non-compliance | Strategic | High | DO-178C compliance demonstrates rigor of safety development process
MIG-22 | MIT-14 | NIS2 cybersecurity framework | Baseline | RO-02 | Cyberattack on PLM infrastructure | Operational | High | NIS2 mandates cybersecurity measures and incident notification
MIG-23 | MIT-14 | NIS2 cybersecurity framework | Baseline | RS-06 | Intellectual property compromise | Strategic | Medium | NIS2 requirements strengthen overall security posture
MIG-25 | MIT-15 | NRC regulatory framework | Baseline | RO-03 | Manufacturing process quality drift | Operational | High | NRC requirements impose high quality standards on processes
MIG-24 | MIT-15 | NRC regulatory framework | Baseline | RS-04 | Regulatory safety non-compliance | Strategic | Critical | Systematic application of NRC framework ensures regulatory compliance
MIG-06 | MIT-04 | PLM Zero Trust architecture | Dedicated | RO-02 | Cyberattack on PLM infrastructure | Operational | Critical | Zero Trust architecture drastically reduces attack surface and lateral movement possibilities
MIG-07 | MIT-04 | PLM Zero Trust architecture | Dedicated | RS-06 | Intellectual property compromise | Strategic | High | PLM security protects intellectual property data
MIG-08 | MIT-05 | Production contingency plan | Dedicated | RS-07 | Insufficient production capacity | Strategic | Medium | Contingency plan allows partially compensating for internal capacity shortfalls
MIG-09 | MIT-05 | Production contingency plan | Dedicated | RS-02 | Series production start delay | Strategic | Medium | Backup subcontractors help maintain schedule in case of problems
MIG-03 | MIT-02 | R&D talent retention program | Dedicated | RO-05 | Key R&D team competency loss | Operational | High | Retention program significantly reduces key expert turnover
MIG-04 | MIT-02 | R&D talent retention program | Dedicated | RS-03 | Loss of competitive technological advantage | Strategic | Medium | Talent retention maintains innovation capability
MIG-05 | MIT-03 | Real-time quality review system | Dedicated | RO-03 | Manufacturing process quality drift | Operational | High | Real-time monitoring enables detecting and correcting drifts before they worsen
MIG-17 | MIT-11 | Shared Innovation program | Inherited | RS-03 | Loss of competitive technological advantage | Strategic | Medium | Access to group innovations accelerates development